## Sheet1
Demand_Ref | Issue_Ref | Package_ID | Item | Demanding_Unit | Theatre | Priority | Last_JSC_Checkpoint | Days_Since_Last_Checkpoint | Time_till_RDD | Chance_of_missing_RDD | Late_Status | Raised_As_Exception? | Exception_Status | Intervention_Action_Taken | Exception_Outcome | Demand_Raised_Date | Pick_and_Packed_Date | Departed_Depot_Date | Arrived_PoE_Date | Departed_PoE_Date | Arrived_PoD_Date | Departed_PoD_Date | Total Orders
1 | 561 | Ano238 | Rubber Bacon | Unit D | Europe | P2 | Arrived PoD | 16 | 29 | 0.45 | Projected On Time | Yes | 1. Triage For Expediting |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 61
2 | 112 | CnO756 | Generic Wooden Towels | Unit B | South America | P2 | Pick & Packed | 17 | 4 | 0.91 | Projected Late | Yes | 5. Exception Closed | Upgraded to Flight | Successful Outcome | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
3 | 778 | TbJ583 | For repair Fresh Keyboard | Unit C | South America | P3 | Arrived PoD | 10 | 51 | 0.17 | Projected On Time | Yes | 5. Exception Closed | Allocated to Earlier Military Flight | Successful Outcome | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 45
4 | 273 | Zkd856 | Computer | Unit D | South America | P1 | Arrived PoD | 20 | 53 | 0.14 | Projected On Time | Yes | 5. Exception Closed | Delivered via. Commercial | Successful Outcome | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 50
5 | 233 | ImE050 | Wooden Chicken | Unit C | Africa | P1 | Arrived PoE | 17 | 44 | 0.24 | Projected On Time | Yes | 5. Exception Closed |  | Successful Outcome | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 50
6 | 412 | nEs329 | Tuna | Unit A | Africa | P1 | Demand Raised | 0 | 17 | 0.56 | Projected Late | Yes | 1. Triage For Expediting |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
7 | 155 | Eni945 | Mouse | Unit B | Africa | P3 | Pick & Packed | 2 | 7 | 0.85 | Projected Late | Yes | 5. Exception Closed |  | Unsuccessful Outcome | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
8 | 970 | RhY243 | Rustic Rubber Bacon | Unit B | Europe | P2 | Arrived PoE | 8 | 49 | 0.19 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
9 | 756 | xEI315 | Sausages | Unit D | Africa | P2 | Departed Depot | 11 | 20 | 0.55 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
10 | 372 | UJp881 | Gently Used Ball | Unit B | Africa | P1 | Pick & Packed | 15 | 3 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
11 | 200 | Zjp996 | Steel Ball | Unit D | South America | P1 | Pick & Packed | 9 | 19 | 0.56 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
12 | 724 | oan164 | Sleek Chair | Unit B | Africa | P2 | Arrived PoD | 4 | 59 | 0.05 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 61
13 | 237 | YzC870 | Granite Salad | Unit C | Africa | P3 | Demand Raised | 18 | 4 | 0.96 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
14 | 815 | Ktq196 | Fresh Soap | Unit D | South America | P2 | Demand Raised | 16 | 9 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
15 | 748 | jUM398 | Steel Chicken | Unit C | Africa | P3 | Pick & Packed | 13 | 2 | 0.95 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
16 | 815 | QVB401 | Gorgeous Plastic Pizza | Unit B | South America | P3 | Demand Raised | 14 | 8 | 0.86 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
17 | 262 | dAN406 | Rubber Table | Unit A | South America | P3 | Arrived PoE | 9 | 55 | 0.12 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 45
18 | 151 | jep163 | Small Pants | Unit D | South America | P2 | Departed Depot | 19 | 12 | 0.82 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
19 | 748 | Ggz188 | Frozen Pants | Unit A | Africa | P3 | Pick & Packed | 19 | 11 | 0.81 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
20 | 257 | hrV237 | Plastic Chicken | Unit C | Europe | P2 | Pick & Packed | 14 | 54 | 0.13 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
21 | 630 | Puq183 | Rubber Sausages | Unit B | Europe | P3 | Departed Depot | 11 | 10 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
22 | 491 | fiY874 | Ball | Unit B | Europe | P2 | Departed Depot | 6 | 9 | 0.86 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
23 | 585 | tGE042 | Bike | Unit A | Europe | P1 | Pick & Packed | 11 | 2 | 0.95 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
24 | 445 | oBw446 | Intelligent Table | Unit A | Africa | P3 | Pick & Packed | 8 | 42 | 0.27 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
25 | 476 | XDA841 | Generic Wooden Sausages | Unit D | Africa | P2 | Pick & Packed | 15 | 27 | 0.47 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
26 | 377 | DWO316 | Metal Bike | Unit D | South America | P2 | Pick & Packed | 18 | 11 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
27 | 246 | ULw325 | Gorgeous Mouse | Unit D | South America | P3 | Pick & Packed | 10 | 6 | 0.93 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
28 | 172 | sTR534 | Intelligent Bike | Unit C | Africa | P1 | Departed Depot | 20 | 30 | 0.43 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
29 | 831 | hYx285 | Soap | Unit B | Europe | P2 | Demand Raised | 19 | 4 | 0.91 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
30 | 468 | DSb975 | Handmade Fresh Pants | Unit B | Europe | P2 | Departed Depot | 4 | 3 | 0.91 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
31 | 696 | gFh231 | Small Granite Chicken | Unit A | South America | P1 | Pick & Packed | 14 | 7 | 0.86 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
32 | 162 | acM041 | Handmade Soft Gloves | Unit B | Africa | P3 | Demand Raised | 7 | 10 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
33 | 765 | xcU280 | Chair | Unit C | Africa | P2 | Demand Raised | 15 | 6 | 0.95 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
34 | 526 | LKe066 | Licensed Granite Salad | Unit E | South America | P2 | Arrived PoE | 6 | 48 | 0.19 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
35 | 230 | ojH850 | Plastic Chips | Unit A | Europe | P1 | Departed Depot | 15 | 3 | 0.97 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
36 | 114 | qBH850 | Fresh Gloves | Unit A | South America | P3 | Arrived PoE | 13 | 33 | 0.34 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 45
37 | 255 | pOQ577 | Wooden Fish | Unit A | Africa | P3 | Pick & Packed | 13 | 12 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
38 | 218 | EBU841 | Gently Used Pants | Unit C | Africa | P1 | Departed Depot | 5 | 26 | 0.47 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
39 | 662 | gbE893 | Concrete Tuna | Unit D | Europe | P1 | Departed Depot | 13 | 56 | 0.12 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
40 | 339 | BwM463 | Gently Used Steel Shoes | Unit A | South America | P2 | Pick & Packed | 10 | 32 | 0.36 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
41 | 352 | AaK917 | Gently Used Granite Car | Unit B | Europe | P3 | Departed PoE | 10 | 46 | 0.22 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 45
42 | 578 | ECt170 | Chicken | Unit E | South America | P2 | Pick & Packed | 4 | 37 | 0.3 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
43 | 898 | UVe740 | Sausages | Unit E | South America | P1 | Demand Raised | 0 | 1 | 0.97 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
44 | 881 | nyy330 | Plastic Bike | Unit E | South America | P1 | Departed Depot | 1 | 3 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
45 | 618 | gNP904 | Plastic Bike | Unit B | South America | P3 | Pick & Packed | 3 | 4 | 0.88 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
46 | 359 | UgO997 | Metal Keyboard | Unit A | Europe | P1 | Pick & Packed | 19 | 18 | 0.56 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
47 | 655 | QSg872 | Tasty Hat | Unit D | Africa | P1 | Pick & Packed | 3 | 61 | 0.02 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
48 | 424 | HjZ775 | Chair | Unit C | Europe | P2 | Pick & Packed | 11 | 21 | 0.53 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
49 | 567 | BEs587 | Tasty Cheese | Unit D | Africa | P1 | Departed Depot | 11 | 9 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
50 | 414 | qPe219 | Wooden Salad | Unit B | Africa | P3 | Pick & Packed | 20 | 47 | 0.21 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
51 | 901 | EGM282 | Generic Chicken | Unit B | Africa | P2 | Pick & Packed | 14 | 10 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
52 | 562 | mAo004 | Handcrafted Keyboard | Unit A | Europe | P1 | Demand Raised | 14 | 8 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
53 | 287 | CXl708 | Fresh Sausages | Unit D | South America | P2 | Pick & Packed | 16 | 36 | 0.31 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
54 | 5 | EIy251 | Wooden Computer | Unit E | Europe | P2 | Departed Depot | 14 | 1 | 0.95 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
55 | 863 | XsL888 | Ergonomic Salad | Unit C | South America | P1 | Pick & Packed | 6 | 1 | 0.89 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
56 | 660 | mHZ554 | Ergonomic Rubber Fish | Unit E | Europe | P3 | Arrived PoE | 0 | 50 | 0.19 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 45
57 | 214 | vzX454 | Steel Salad | Unit C | South America | P1 | Demand Raised | 5 | 43 | 0.26 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
58 | 914 | xyc181 | Used Bike | Unit C | Africa | P1 | Departed Depot | 5 | 1 | 0.98 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
59 | 522 | Wyj712 | Ball | Unit B | Europe | P3 | Demand Raised | 4 | 2 | 0.89 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
60 | 953 | Hsf734 | Ball | Unit B | South America | P1 | Departed Depot | 9 | 2 | 0.91 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
61 | 683 | IrD956 | Frozen Shoes | Unit E | Africa | P3 | Departed Depot | 2 | 12 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
62 | 950 | vIK152 | Rubber Pizza | Unit A | Africa | P3 | Demand Raised | 17 | 12 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
63 | 384 | BYl756 | Bacon | Unit B | South America | P2 | Demand Raised | 1 | 57 | 0.1 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
64 | 315 | YWk971 | Pants | Unit D | Africa | P3 | Pick & Packed | 19 | 31 | 0.4 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
65 | 825 | SQc689 | Granite Chips | Unit C | Europe | P3 | Departed Depot | 3 | 9 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
66 | 512 | RfI129 | Sausages | Unit B | South America | P2 | Departed Depot | 12 | 16 | 0.56 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
67 | 634 | GEE047 | Handcrafted Soft Bike | Unit D | South America | P1 | Arrived PoD | 13 | 22 | 0.52 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 50
68 | 389 | ywp684 | New Shoes | Unit D | South America | P2 | Departed Depot | 9 | 6 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
69 | 541 | iHL115 | Concrete Car | Unit E | Europe | P2 | Pick & Packed | 1 | 45 | 0.22 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
70 | 696 | cBX614 | Handcrafted Plastic Cheese | Unit E | Africa | P2 | Departed Depot | 8 | 6 | 0.87 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
71 | 882 | pyi055 | Small Pants | Unit D | Europe | P1 | Departed PoE | 6 | 40 | 0.27 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 50
72 | 102 | WAU109 | Licensed Metal Hat | Unit C | Europe | P2 | Arrived PoE | 14 | 12 | 0.77 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
73 | 998 | mHD544 | Soft Sausages | Unit A | Africa | P3 | Arrived PoE | 3 | 7 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 45
74 | 752 | niu929 | New Gloves | Unit E | Africa | P1 | Arrived PoD | 16 | 12 | 0.8 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 50
75 | 600 | plC182 | Pants | Unit E | Africa | P1 | Arrived PoE | 18 | 13 | 0.76 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 50
76 | 742 | LFn112 | Fantastic Plastic Salad | Unit E | South America | P2 | Demand Raised | 0 | 35 | 0.33 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
77 | 500 | urt281 | Computer | Unit E | South America | P1 | Arrived PoD | 10 | 10 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 50
78 | 880 | pGr435 | Computer | Unit C | Africa | P2 | Departed PoE | 13 | 28 | 0.46 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 61
79 | 630 | PxX588 | Rubber Bike | Unit C | Europe | P2 | Arrived PoD | 6 | 23 | 0.52 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 61
80 | 199 | MLT969 | Refined Salad | Unit D | South America | P3 | Pick & Packed | 13 | 38 | 0.29 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
81 | 35 | Pic130 | Shirt | Unit E | South America | P2 | Arrived PoE | 14 | 6 | 0.89 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
82 | 951 | oYT647 | Ergonomic Rubber Mouse | Unit A | Europe | P2 | Arrived PoD | 2 | 15 | 0.75 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 61
83 | 513 | Dea160 | Hat | Unit B | Africa | P1 | Arrived PoE | 13 | 6 | 0.85 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 50
84 | 495 | Adw833 | Wooden Hat | Unit D | Africa | P2 | Arrived PoE | 10 | 11 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
85 | 859 | eLj819 | Mouse | Unit A | South America | P3 | Departed PoE | 5 | 60 | 0.04 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 45
86 | 747 | uhE381 | Ergonomic Fresh Computer | Unit B | Europe | P3 | Departed PoE | 5 | 52 | 0.14 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 45
87 | 241 | XkX365 | Generic Fresh Pants | Unit A | Europe | P1 | Demand Raised | 17 | 39 | 0.28 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
88 | 896 | wyt008 | Unbranded Cheese | Unit D | Europe | P2 | Arrived PoE | 19 | 10 | 0.81 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
89 | 907 | ZKl612 | Car | Unit A | Africa | P2 | Departed Depot | 0 | 11 | 0.84 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
90 | 876 | hAV405 | Salad | Unit B | South America | P2 | Departed Depot | 4 | 14 | 0.76 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
91 | 631 | mHX798 | New Pizza | Unit B | Africa | P2 | Departed PoE | 7 | 58 | 0.09 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 61
92 | 649 | wJR876 | Generic Steel Fish | Unit B | Africa | P1 | Departed Depot | 2 | 1 | 0.98 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
93 | 675 | Ndn660 | Salad | Unit C | Europe | P3 | Arrived PoE | 18 | 10 | 0.78 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 45
94 | 552 | vSt059 | Keyboard | Unit C | South America | P1 | Demand Raised | 9 | 41 | 0.27 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
95 | 112 | RLY477 | Cheese | Unit B | Europe | P3 | Arrived PoD | 11 | 11 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 45
96 | 657 | UlT318 | Wooden Salad | Unit B | South America | P3 | Pick & Packed | 20 | 25 | 0.47 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
97 | 536 | kWn253 | Steel Keyboard | Unit B | Europe | P2 | Demand Raised | 15 | 34 | 0.33 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
98 | 66 | gQe426 | Ball | Unit E | Europe | P1 | Arrived PoD | 14 | 11 | 0.78 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-14 22:33:00 |  | 50
99 | 952 | oUB939 | Used Granite Gloves | Unit E | Europe | P2 | Arrived PoE | 3 | 2 | 0.93 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 |  |  |  | 61
100 | 114 | qBH850 | Fresh Gloves | Unit A | South America | P3 | Demand Raised | 13 | -1 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
101 | 536 | kWn253 | Steel Keyboard | Unit B | Europe | P2 | Demand Raised | 15 | -1 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
102 | 233 | ImE050 | Wooden Chicken | Unit C | Africa | P1 | Demand Raised | 17 | -1 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
103 | 262 | dAN406 | Rubber Table | Unit A | South America | P3 | Demand Raised | 9 | -1 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
104 | 384 | BYl756 | Bacon | Unit B | South America | P2 | Demand Raised | 1 | -1 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
105 | 634 | GEE047 | Handcrafted Soft Bike | Unit D | South America | P1 | Pick & Packed | 13 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
106 | 561 | Ano238 | Rubber Bacon | Unit D | Europe | P2 | Pick & Packed | 16 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
107 | 339 | BwM463 | Gently Used Steel Shoes | Unit A | South America | P2 | Pick & Packed | 10 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
108 | 742 | LFn112 | Fantastic Plastic Salad | Unit E | South America | P2 | Demand Raised | 0 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
109 | 578 | ECt170 | Chicken | Unit E | South America | P2 | Pick & Packed | 4 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
110 | 541 | iHL115 | Concrete Car | Unit E | Europe | P2 | Pick & Packed | 1 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
111 | 778 | TbJ583 | For repair Fresh Keyboard | Unit C | South America | P3 | Departed PoD | 10 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-21 19:11:00 | 2024-12-22 22:33:00 | 2024-12-24 01:55:00 | 2024-12-27 05:17:00 | 45
112 | 257 | hrV237 | Plastic Chicken | Unit C | Europe | P2 | Departed PoD | 14 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-17 19:11:00 | 2024-12-18 22:33:00 | 2024-12-20 01:55:00 | 2024-12-23 05:17:00 | 61
113 | 662 | gbE893 | Concrete Tuna | Unit D | Europe | P1 | Departed PoE | 13 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 50
114 | 724 | oan164 | Sleek Chair | Unit B | Africa | P2 | Departed PoD | 4 | -2 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-16 19:11:00 | 2024-12-17 22:33:00 | 2024-12-19 01:55:00 | 2024-12-22 05:17:00 | 61
115 | 657 | UlT318 | Wooden Salad | Unit B | South America | P3 | Departed PoD | 20 | -3 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-20 19:11:00 | 2024-12-21 22:33:00 | 2024-12-23 01:55:00 | 2024-12-26 05:17:00 | 45
116 | 287 | CXl708 | Fresh Sausages | Unit D | South America | P2 | Departed PoD | 16 | -3 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-15 19:11:00 | 2024-12-16 22:33:00 | 2024-12-18 01:55:00 | 2024-12-21 05:17:00 | 61
117 | 526 | LKe066 | Licensed Granite Salad | Unit E | South America | P2 | Demand Raised | 6 | -3 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
118 | 631 | mHX798 | New Pizza | Unit B | Africa | P2 | Departed PoE | 7 | -3 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 61
119 | 880 | pGr435 | Computer | Unit C | Africa | P2 | Departed PoE | 13 | -4 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 61
120 | 970 | RhY243 | Rustic Rubber Bacon | Unit B | Europe | P2 | Demand Raised | 8 | -4 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 61
121 | 512 | RfI129 | Sausages | Unit B | South America | P2 | Departed PoE | 12 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 61
122 | 630 | PxX588 | Rubber Bike | Unit C | Europe | P2 | Departed PoD | 6 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-14 19:11:00 | 2024-12-15 22:33:00 | 2024-12-17 01:55:00 | 2024-12-20 05:17:00 | 61
123 | 172 | sTR534 | Intelligent Bike | Unit C | Africa | P1 | Departed PoE | 20 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 |  |  | 50
124 | 882 | pyi055 | Small Pants | Unit D | Europe | P1 | Departed Depot | 6 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
125 | 352 | AaK917 | Gently Used Granite Car | Unit B | Europe | P3 | Departed Depot | 10 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
126 | 747 | uhE381 | Ergonomic Fresh Computer | Unit B | Europe | P3 | Departed Depot | 5 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
127 | 655 | QSg872 | Tasty Hat | Unit D | Africa | P1 | Departed PoD | 3 | -5 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-13 19:11:00 | 2024-12-14 22:33:00 | 2024-12-16 01:55:00 | 2024-12-19 05:17:00 | 50
128 | 412 | nEs329 | Tuna | Unit A | Africa | P1 | Demand Raised | 0 | -7 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
129 | 218 | EBU841 | Gently Used Pants | Unit C | Africa | P1 | Departed Depot | 5 | -7 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
130 | 315 | YWk971 | Pants | Unit D | Africa | P3 | Departed PoD | 19 | -7 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-19 19:11:00 | 2024-12-20 22:33:00 | 2024-12-22 01:55:00 | 2024-12-25 05:17:00 | 45
131 | 552 | vSt059 | Keyboard | Unit C | South America | P1 | Demand Raised | 9 | -7 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
132 | 660 | mHZ554 | Ergonomic Rubber Fish | Unit E | Europe | P3 | Demand Raised | 0 | -7 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 45
133 | 273 | Zkd856 | Computer | Unit D | South America | P1 | Departed PoD | 20 | -7 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-15 01:55:00 | 2024-12-18 05:17:00 | 50
134 | 500 | urt281 | Computer | Unit E | South America | P1 | Departed PoD | 10 | -10 | 1 | Already Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-15 01:55:00 | 2024-12-17 05:17:00 | 50
135 | 199 | MLT969 | Refined Salad | Unit D | South America | P3 | Departed PoD | 13 | 25 | 0.43 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-18 19:11:00 | 2024-12-19 22:33:00 | 2024-12-21 01:55:00 | 2024-12-24 05:17:00 | 45
136 | 859 | eLj819 | Mouse | Unit A | South America | P3 | Departed Depot | 5 | 31 | 0.33 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
137 | 359 | UgO997 | Metal Keyboard | Unit A | Europe | P1 | Departed PoD | 19 | 24 | 0.47 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 15:49:00 | 2024-12-12 19:11:00 | 2024-12-13 22:33:00 | 2024-12-15 01:55:00 | 2024-12-16 05:17:00 | 50
138 | 476 | XDA841 | Generic Wooden Sausages | Unit D | Africa | P2 | Pick & Packed | 15 | 41 | 0.32 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 61
139 | 445 | oBw446 | Intelligent Table | Unit A | Africa | P3 | Pick & Packed | 8 | 44 | 0.25 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
140 | 414 | qPe219 | Wooden Salad | Unit B | Africa | P3 | Pick & Packed | 20 | 48 | 0.21 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 45
141 | 756 | xEI315 | Sausages | Unit D | Africa | P2 | Departed Depot | 11 | 57 | 0.15 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
142 | 214 | vzX454 | Steel Salad | Unit C | South America | P1 | Demand Raised | 5 | 53 | 0.32 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
143 | 200 | Zjp996 | Steel Ball | Unit D | South America | P1 | Pick & Packed | 9 | 40 | 0.27 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | [5 empty] | 50
144 | 241 | XkX365 | Generic Fresh Pants | Unit A | Europe | P1 | Demand Raised | 17 | 30 | 0.48 | Projected On Time |  |  |  |  | 2024-12-09 09:05:00 | [6 empty] | 50
145 | 649 | wJR876 | Military Boots | Unit B | Africa | P1 | Pick & Packed | 4 | 15 | 0.74 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
146 | 650 | xEI315 | Car Engine | Unit B | Africa | P1 | Pick & Packed | 5 | 10 | 0.84 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
147 | 651 | wJR876 | Ration Packets | Unit B | Africa | P1 | Pick & Packed | 6 | 16 | 0.68 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
148 | 652 | wJR876 | Uniform | Unit B | Africa | P1 | Pick & Packed | 5 | 12 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 50
150 | 653 | nEs329 | Military Boots | Unit B | Africa | P2 | Pick & Packed | 4 | 15 | 0.74 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
151 | 654 | wJR876 | Car Engine | Unit B | Africa | P2 | Pick & Packed | 5 | 10 | 0.84 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
152 | 655 | vzX454 | Ration Packets | Unit B | Africa | P2 | Pick & Packed | 6 | 16 | 0.68 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61
153 | 660 | urt281 | Uniform | Unit B | Africa | P3 | Pick & Packed | 5 | 12 | 0.79 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
154 | 659 | xEI315 | Ration Packets | Unit B | Africa | P3 | Pick & Packed | 6 | 16 | 0.68 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
155 | 658 | wJR876 | Car Engine | Unit B | Africa | P3 | Pick & Packed | 5 | 10 | 0.84 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
156 | 657 | nEs329 | Military Boots | Unit B | Africa | P3 | Pick & Packed | 4 | 15 | 0.74 | Projected Late |  |  |  |  | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 45
157 | 656 | wJR876 | Uniform | Unit B | Africa | P2 | Pick & Packed | 5 | 12 | 0.79 | Projected Late | Yes | 1. Triage For Expediting |  | Unsuccessful Outcome | 2024-12-09 09:05:00 | 2024-12-10 12:27:00 | 2024-12-11 08:48:00 |  |  |  |  | 61